## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database instance | Junpeng Wen | 2024-02-29 | 2024-03-05 | 3 | 2
Create <Demographics> dimension | Chenxiao Ze | 2024-03-11 | 2024-03-15 | 2 | 1
Create <NutrientIntake> dimension | Chenxiao Ze | 2024-03-11 | 2024-03-15 | 2 | 1
Create <PhysicalActivity> dimension | Yongquan Long | 2024-03-11 | 2024-03-17 | 2 | 1
Create <MedicalCondition> dimension | Yongquan Long | 2024-03-11 | 2024-03-17 | 2 | 1
Staging of dimension <Demographics> | Chenxiao Ze | 2024-03-11 | 2024-03-15 | 2 | 1
Staging of dimension <NutrientIntake> | Chenxiao Ze | 2024-03-11 | 2024-03-15 | 2 | 1
Staging of dimension <PhysicalActivity> | Yongquan Long | 2024-03-11 | 2024-03-17 | 2 | 1
Staging of dimension <MedicalCondition> | Yongquan Long | 2024-03-11 | 2024-03-17 | 2 | 1
Surrogate key pipeline | Junpeng Wen | 2024-03-11 | 2024-03-19 | 1 | 2
Staging of fact table – including FKs and measures | Junpeng Wen | 2024-03-16 | 2024-03-19 | 2 | 2
Data quality handling and reporting | Junpeng Wen,Chenxiao Ze, Yongquan Long | 2024-03-20 | 2024-03-26 | 10 | 8
Others – if any